## Team
Initials | First | Last | Email | GitHub Username
RA | Rafif | Arab | rarab@stevens.edu | rafif353
MA | Maha | Alidrisi | malidrisi@stevens.edu | malidrisi
SS | Saloni | Setia | ssetia@stevens.edu | ssetia93
|  |  | GitHub Repository: | SSW-555-GEDCOM

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Dates before current date | RA | Done
2 | US02 | Birth before marriage | SS | Done
1 | US03 | Birth before death | SS | Done
4 | US04 | Marriage before divorce | RA | Initiated
3 | US05 | Marriage before death | SS | Done
4 | US06 | Divorce before death | RA | Initiated
1 | US07 | Less then 150 years old | MA | Done
| US08 | Birth before marriage of parents
| US09 | Birth before death of parents
2 | US10 | Marriage after 14 | SS | Done
| US11 | No bigamy
| US12 | Parents not too old
| US13 | Siblings spacing
| US14 | Multiple births less than 5
3 | US15 | Fewer than 15 siblings | SS | Done
2 | US16 | Male last names | MA | Done
| US17 | No marriages to descendants
| US18 | Siblings should not marry
| US19 | First cousins should not marry
| US20 | Aunts and uncles
3 | US21 | Correct gender for role | RA | Done
2 | US22 | Unique IDs | RA | Done
1 | US23 | Unique name and birth date | SS | Done
4 | US24 | Unique families by spouses | MA | Initiated
4 | US25 | Unique first names in families | MA | Initiated
| US26 | Corresponding entries
1 | US27 | Include individual ages | RA | Done
4 | US28 | Order siblings by age | SS | Done
1 | US29 | List deceased | MA | Done
4 | US30 | List living married | SS | Done
3 | US31 | List living single | RA | Done
| US32 | List multiple births
| US33 | List orphans
| US34 | List large age differences
3 | US35 | List recent births | MA | Done
2 | US36 | List recent deaths | MA | Done
| US37 | List recent survivors
2 | US38 | List upcoming birthdays | RA | Done
3 | US39 | List upcoming anniversaries | MA | Done
| US40 | Include input line numbers
| US41 | Include partial dates
| US42 | Reject illegitimate dates

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2016-09-20 | 42 | 0 | 0 | 0 | 0
2016-10-04 | 36 | 6 | 104 | 390 | 16
2016-10-12 | 30 | 6 | 137 | 208 | 9.5192
2016-11-01 | 24 | 6 | 178 | 143 | 17.2028

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Date before current date | RA | Done | 100 | 240 | 22 | 120 | 2016-10-01
T01.01 | Find dates (birth, marriage, divorce, death)
T01.02 | Compare date and current date
US03 | Birth before death | SS | Done | 100 | 240 | 20 | 30 | 2016-10-03
T03.01 | Store birth date
T03.02 | Store death date
T03.03 | Compare birth and death dates
US07 | Less then 150 years old | MA | Done | 100 | 240 | 12 | 70 | 2016-09-30
T07.01 | Store birth date of every individual
T07.02 | Store death date of every dead individual
T07.03 | Compare death date and birth date for dead individuals(difference should be less than 150)
T07.04 | Compare birthdate and current date for living individuals(difference should be less than 150)
US23 | Unique name and birthdate | SS | Done | 100 | 240 | 17 | 40 | 2016-10-03
T23.01 | Store name of every individual
T23.02 | Store birthdate of every individual
T23.03 | Compare name and birthdate of every new inidvidual with existing records
US27 | Include individual ages | RA | Done | 100 | 240 | 16 | 90 | 2016-10-03
T27.01 | Store current age of every individual
US29 | List deceased | MA | Done | 100 | 240 | 17 | 40 | 2016-10-03
T29.01 | Find every individual with a death date
T29.02 | Store their name in a GEDCOM file
Review Results
Keep doing:
Meeting twice every week.
Commiting progress to github
Avoid:
Avoid delay

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US16 | Male last names | MA | Done | 17 | 80 | 13 | 15 | 2016-10-11
T16.01 | find SEX =M
T16.02 | Print Last Name
US22 | Unique IDs | RA | Done | 15 | 90 | 21 | 30 | 2016-10-11
T22.01 | Find ID for individual and family
T22.02 | Check no duplicate IDs
US36 | List recent deaths | MA | Done | 30 | 90 | 17 | 13 | 2016-10-12
T36.01 | find Dead individuals
T36.02 | compare Death date to today
T36.03 | if less than # months print Name
US38 | List upcoming birthdays | RA | Done | 20 | 90 | 26 | 60 | 2016-10-12
T38.01 | Find Birthdate for each alive individual
T38.02 | Check upcoming birthday for next month
US02 | Birth before marriage | SS | Done | 30 | 60 | 28 | 60 | 2016-10-12
T02.01 | Find married Individuals
T02.02 | Find their birth date
T02.03 | Find their marriage date
T02.04 | Check if birth happens before marriage
US10 | Marriage after 14 | SS | Done | 25 | 60 | 32 | 30 | 2016-10-12
T10.01 | Find married Individuals
T10.02 | Find their birth date
T10.03 | Find their marriage date
T10.04 | Check if marriage date is after 14 years of birth
Review Results:
Keep doing:
Meeting twice every week.
Commiting progress to github
Pair Programming
Updating existing code to incorporate new requirements.
Avoid:
Avoid delay
Avoid miscommunication
Procastination

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US05 | Marriage before death | SS | Done | 30 | 60 | 57 | 60 | 2016-10-25
T05.01 | Find married individuals
T05.02 | Find their marriage date
T05.03 | Find their death date
T05.04 | Marriage date should come before death date
US15 | Fewer than 15 siblings | SS | Done | 30 | 60 | 14 | 15 | 2016-10-13
T15.01 | Count number of children in a family
T15.02 | count should be less than 15
US21 | Correct gender for role | RA | Done | 35 | 60 | 39 | 20 | 2016-10-22
T21.01 | find husband and wife
T21.02 | check correct gender
US31 | List living single | RA | Done | 30 | 60 | 25 | 10 | 2016-10-22
T31.01 | Check age over 30
T31.02 | check single people
US35 | List recent births | MA | Done | 30 | 60 | 14 | 8 | 2016-10-22
T35.01 | find birthdate
T35.02 | compare birth date to today
T35.03 | if less than # months print Name
US39 | List upcoming anniversaries | MA | Done | 35 | 60 | 29 | 30 | 2016-10-22
T39.01 | Find Marriage date for each family
T39.02 | compare to today
T39.03 | print marriage date for next month
Review Results:
Keep doing:
Meeting twice every week.
Commiting progress to github
Review each others code
Adding test cases
Avoid:
Avoid delay
Avoid miscommunication
Procastination
Avoid changing the original gedcom to test US

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US28 | Order siblings by age | SS | Done | 30 | 60 | 28 | 40 | 2016-10-26
T28.01 | Find children in the family
T28.02 | Find their birth date
T28.03 | List in order of their birth
US30 | List living married | SS | Done | 30 | 60 | 14 | 10 | 2016-10-25
T30.01 | Find married individuals
T30.02 | Check if they're living or dead
US04 | Marriage before divorce | RA | Initiated | 30 | 30
T04.01 | Find mariage date
T04.02 | Find divorce date
T04.03 | Check if divorce happens before marriage
US06 | Divorce before death | RA | Initiated | 30 | 30
T06.01 | Find married Individuals
T06.02 | Find their divorce date
T06.03 | Find death date
T06.04 | Check if death happens before divorce
US24 | Unique families by spouses | MA | Initiated | 35 | 40
T24.01 | define a list for each family names
T24.02 | add husband and wife names
T24.03 | add children names
T24.04 | check if sthe list has repeated name
US25 | Unique first names in families | MA | Initiated | 35 | 40
T25.01 | define a list for each family names
T25.02 | add husband and wife names
T25.03 | add children names
T25.04 | check if sthe list has repeated name

## Stories
Story ID | Story Name | Story Description | status
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date | y
US02 | Birth before marriage | Birth should occur before marriage of an individual | y
US03 | Birth before death | Birth should occur before death of an individual | y
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse | y
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people | y
US08 | Birth before marriage of parents | Child should be born after marriage of parents (and before their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses | y
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart
US14 | Multiple births less than 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family | y
US16 | Male last names | All male members of a family should have the same last name | y
US17 | No marriages to descendants | Parents should not marry any of their descendants
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique | y
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file | y
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in those family records, and all individual roles (spouse, child) specified in family records should have corresponding entries in those individual's records
US27 | Include individual ages | Include person's current age when listing individuals | y
US28 | Order siblings by age | List siblings in families by age | y
US29 | List deceased | List all deceased individuals in a GEDCOM file | y
US30 | List living married | List all living married people in a GEDCOM file | y
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days | y
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days | y
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)